## Slide 1
Conduite des Projets Scientifiques
CONDUCTING Scientific Projects
Course
Instructor: |  |  |  | 
 | Dr. Belkacem KHALDI |  |  | 
 | b.khaldi@esi-sba.dz |  | belkacem_khaldi | 
 | Belkacem_Khaldi |  | Khaldi Belkacem | 

## Slide 2
Part II
Conducting Scientific Projects
Scientific Project Management

## Slide 3
Scientific Project Management
Conducting Scientific Projects
    What is a research?
About Scientific Research:
Attempt to find out information in a systematically and scientific manner.
The systematic collection, analysis and interpretation of data to answer a certain question or solve a problem.
The process of discovering new knowledge or of synthesis of existing knowledge into a form useful for a stated purpose.

## Slide 4
Scientific Project Management
Conducting Scientific Projects
    Why do we conduct Research Projects?
About Scientific research:
To invent new things
To solve a prevailing problem
To support development programmes of a country
To uplift living standards
Because we are inquisitive about things happening around us

## Slide 5
Scientific Project Management
Conducting Scientific Projects
About Scientific Research Proposal:
  A document that contains details about a scientific investigation to be carried out (i.e., not started yet)
  It contains details about:
    The problem to be studied
    How the investigation will be conducted
    Expected results and contribution
    Work schedule / Time frame
    Budget (for those seeking funds)
    What is a research proposal?

## Slide 6
Scientific Project Management
Conducting Scientific Projects
    Main purpose of a research proposal?
It is to show that
  the problem you propose to investigate is significant enough to warrant the investigation,
  the method you plan to use is suitable and feasible, and
  the results are likely to prove fruitful and will make an original [or significant] contribution.
  In short, what you are answering is 'will it work?‘
About Scientific Research Proposal:

## Slide 7
Scientific Project Management
Conducting Scientific Projects
    Research Plan
Title
Background to the research
Statement of problem
Objectives of research
Literature review
Methodology
Work schedule
Guide to Research Proposal Writing:
Budget Estimation

## Slide 8
Scientific Project Management
Conducting Scientific Projects
    Title
Good titles identify the field(s) of research and indicate the kind of results to be obtained
Avoid
  Too long titles
  Too general or vague titles
Guide to Research Proposal Writing:

## Slide 9
Scientific Project Management
Conducting Scientific Projects
    Background to the research and problem statement
The key effort is to make the reviewers/readers understand
  What is the problem
  Why is the problem important
Problem statement answers one primary question: ‘‘Why do this project?’’
  The emphasis is on the ‘‘why’’
To answer this question, proposal writers must
  Define the problem and
  Document its existence
Guide to Research Proposal Writing:

## Slide 10
Scientific Project Management
Conducting Scientific Projects
    Background to the research and problem statement
Guide to Research Proposal Writing:
Your statement of the problem should quickly:
  summarize the problem from the vantage point of the readers,
  show your familiarity with prior research or work on the problem,
  justify why this problem should be investigated
Do not assume that everyone sees the problem as clearly as you do
  even if the problem is obvious, your readers want to know how clearly you can state it

## Slide 11
Scientific Project Management
Conducting Scientific Projects
    Background to the research and problem statement
Guide to Research Proposal Writing:
Describes the broader context and issues
Links the broader context and issues to the problem to be investigated
Problem statement

## Slide 12
Scientific Project Management
Conducting Scientific Projects
    Research objectives
Guide to Research Proposal Writing:
Objectives describe the purpose of the study
Must be
  specific
  clear
  logical
  immediate (have a time frame)
  concise, and
  achievable (measurable)

## Slide 13
Scientific Project Management
Conducting Scientific Projects
    Research objectives
Guide to Research Proposal Writing:
May have two sections: general and specific objectives
Or split study into parts/sections, and for each section a statement of its study objectives
  But ensure the sections are related to one another to solve or investigate the overall problem
Hypothesis to be tested
  Expected results
    What you expect/believe the results would be

## Slide 14
Scientific Project Management
Conducting Scientific Projects
    Literature review
Guide to Research Proposal Writing:
Important to
  Identify,
  Evaluate,
  Interpret,
  Assimilate,
  and Summarize all studies relevant to your study
Do not put all past studies into your proposal!
  Select those really important (and current) studies

## Slide 15
Scientific Project Management
Conducting Scientific Projects
    Methodology
Guide to Research Proposal Writing:
Lab analysis methodology
  Site location and its general characteristics
  Equipment and software needed
Experimental design and layout
  Ensure robustness of statistical analyses
  Statistical methods for data analysis

## Slide 16
Scientific Project Management
Conducting Scientific Projects
    Methodology
Guide to Research Proposal Writing:
Data collection
  When will it begin and end
  Frequency of data collection
  What and how will be the data be collected
    Type of data to be collected
  How much data are needed

## Slide 17
Scientific Project Management
Conducting Scientific Projects
    Work schedule
Guide to Research Proposal Writing:
Describes the time frame for your work
  When you will begin and end each part of your study
Create a Gantt chart to depict your schedule

## Slide 18
Scientific Project Management
Conducting Scientific Projects
    Work schedule
Guide to Research Proposal Writing:
 | YEAR 1 |  |  |  |  |  |  |  |  |  |  |  | YEAR 2 |  |  |  |  |  |  |  |  |  |  | 
ACTIVITIES | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Activity 1 | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Activity 2 |  |  |  |  | x | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  | 
Activity 3 |  |  |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Activity 4 |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x |  |  |  | 
Activity 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x

## Slide 19
Scientific Project Management
Conducting Scientific Projects
    Budget Estimation
Guide to Research Proposal Writing:
If you are applying for research funding, you have to include a detailed budget that shows how much each part of the project will cost.
Make sure to check what type of costs the funding body will agree to cover.
For each item, include:
  Cost: exactly how much money do you need?
  Justification: why is this cost necessary to complete the research?
  Source: how did you calculate the amount?

## Slide 20
Scientific Project Management
Conducting Scientific Projects
    Budget Estimation
Guide to Research Proposal Writing:
To determine your budget, think about:
  Travel costs: do you need to go to specific locations to collect data? How will you get there, how long will you spend there, and what will you do there?
  Materials: do you need access to any tools or technologies? Are there training or installation costs?

## Slide 21
Scientific Project Management
Conducting Scientific Projects
    Budget Estimation
Guide to Research Proposal Writing:
  Assistance: do you need to hire research assistants for the project? What will they do and how much will you pay them? Will you outsource any other tasks such as transcription?
  Time: How much will you need to cover the time spent on the research?

## Slide 22
Scientific Project Management
Conducting Scientific Projects
Most Funding Researches Opportunities:
  Georg Forster Research Fellowship by Humboldt Foundation, Germany.
  Marie Skłodowska-Curie Actions by the European Union.

## Slide 23
Computer Science Higher School of Sidi-Bel-Abbes
S
a
m
p
l
e
T
e
x
t
S
a
m
p
l
e
T
e
x
t
S
a
m
l
e
T
e
x
t
S
a
m
p
l
e
T
e
x
t
a
m
p
l
e
T
e
x
t
Thanks for your attention
Conducting Scientific Projects
By Dr. Belkacem KHALDI
Notes: Basic Definitions
Portfolio: A combination of projects and programs that help achieve an overarching strategy.
Program: A group of projects that focuses on an area of a portfolio
Project: A specific set of tasks that need to be complete to achieve the goals of the program / portfolio.
As an example .
 Your Education Goals might be one of your “Portfolios”
 Attending Graduate School might be one of your “Programs”
 Completing your dissertation or your capstone might be one of your “Projects”